## Sheet1
DATE: | [8 empty] | Interim Life Safety Measures NLC | [13 empty] | Environmental Risk Factors
Project: Current SOC Project No. GC Supervisor: Project Manger: Submitted By: Director of Plant Ops Approved By: __X__Safety __X__ Plant Ops ______Inf Ctrl ______Security ______ Risk Mgmt __X__ EC Committee | Level of Impact | 1) Ensure egress via periodic inspections | 2a) Alternate access is provided Emergency Forces | 2b) Notification of Emergency forces | 3) Ensure alternative operational life safety systems | 4) Temporary construction barriers | 5) Additional fire fighting equipment | 6) Prohibit smoking | 7) Control combustible loading | 8a) Conduct additional fire drill in adjacent area | 8b) Conduct additional fire drill in affected area | 9) Increase hazard surveillance of area | 10) Compartmentation training of personnel | 11a) Conduct task specific training on life safety | 11b) Conduct additional training for response team | 12) Alert staff in affected area | 13) Provide signage to reinforce education | 14) Does not warrant any additional measure with existing saf-guards in place | 15) No additional measures deemed necessary based on minimal impact | 16) Other: Install closer onto door to ensure that it closes | 17) Other: | 18) Other: | a) Air Quality | b) Infection Control | c) Utilities | d) Noise | e) Vibration | f) Emergency Procedures
Existing / Probable Code Deficiencies
Corridor room door latching problem | NA
Lacking a code compliant smoke barrier | NA
Fire exit stairs discharge improperly | NA
Excessive travel distance to exit | NA
Lack of two remote exits | NA
Nonconforming bldg. construction type | NA
Waiting area missing smoke detector | MI | [10 empty] | X |  |  |  | X
Improperly protected vertical openings | NA
Large penetrations in fire barriers | NA
Corridor walls do not extend to the structure | NA
Hazardous areas not properly protected | NA
Fire Alarm inoperative / malfunction | NA
Suppression inactive / malfunction | NA
Exposed structural steel req's fire proofing | MI | [17 empty] | X
Inappropriate / Insufficient exit signage | NA
PPE cabinets project > 3.5" into corridor | MI | [17 empty] | X
Corridor door extends beyond 7" when fully open | MI
Small penetrations in corridor walls | MI | [17 empty] | X
Construction Related Issues
Blocking off an approved exit | NA
Rerouting of traffic to emergency room | NA
Major renovation of an occupied area | NA
Replacing fire alarm system | NA
Installing sprinkler system | NA
Significantly modifying smoke/fire barrier walls | NA
Adding and addition to an existing structure | NA
Other Issue or Deficiency | NA
Maintenance and Testing
Taking a fire alarm system out-of-service | NA
Taking a sprinkler system out-of-service | NA
Disconnection of alarm devices | NA
Device(s) failed, out-of-service / describe below | NA
Fire Dampers are inaccessable & cannnot be tested | MI | [11 empty] | X |  |  | X
Other Issue or Deficiency | NA
SI= Significant Impact, MO= Moderate Impact, MI= Minimal Impact, NA= Not Applicable *Note: When determining the Impact Level/ Risk, consider the volume of like deficiencies, their locations, as well as length of time necessary to repair/correct
Note on M2: A memo has been sent to the affected area manager to ensure that all staff are reminded to keep vigilant observation for smoke and fire in this area.
Note on N2: Staff are reminded to close all corridor doors whenever the fire alarm is activated. This is monitored and reinforced during drills. A memo has been sent to all unit managers and dept heads to assure this is communicated to staff.
Note on Q2: Memo sent out to all dept heads, reminding to ensure all doors are closed whenever the fire alarm is activated.